## Charter
PROJECT CHARTER
PROJECT TITLE		FairyDust Art Website Development		DESCRIPTION		User-friendly e-commerce website to expand sales channels and enhance brand visibility for resin products.
BUSINESS NEEDS				CORE TEAM MEMBERS				KEY STAKEHOLDERS
Establish a strong online presence to reach a broader audience interested in resin products.				NAME		ROLE		NAME		ROLE
Increase sales by offering a convenient and visually appealing e-commerce platform for customers.				Muiz Lambe		Project Manager		Amar Sherkar		GMO
Gain a competitive edge with a user-friendly website, enhancing the brand's image in the market.				Poonam Indalkar		Web Developer		Naved Shaikh		CEO
Improve customer satisfaction with features like easy navigation and secure checkout.				Arshiya Shaikh		UI/UX Designer
Utilize analytics tools to gather insights into customer behavior and sales patterns for informed decision-making.				Safa Dalvi		Quality Assurance Tester
Enhance the brand image by presenting resin products attractively and providing accurate product information.				Swaroop Bidkar		Marketing Specialist
OBJECTIVES
Develop an e-commerce website for selling high-quality resin products. / Enhance brand visibility and customer engagement. / Provide a seamless and secure online shopping experience.
GOALS					SUMMARY PROJECT STATUS
To establish a dynamic and visually appealing e-commerce platform that not only showcases our range of high-quality resin products but also provides a seamless and secure online shopping experience. The goal is to significantly increase online sales, enhance brand recognition, and elevate customer satisfaction by delivering a user-friendly website that aligns with industry best practices and sets us apart in the market.					Project Start Date			27/12/23
					Project End Date			03/04/24
					Budget			$45000
					Deployment			10/04/24
SCOPE			OPPORTUNITY				MIESTONES		STATUS	DUE	DONE
Design and develop a mobile-responsive e-commerce website featuring a comprehensive product catalog, secure payment gateway, and user-friendly interface for seamless navigation and optimal customer experience.			Capitalizing on the growing demand for resin products, the website presents a unique opportunity to expand market reach, elevate brand visibility, and leverage data insights to enhance customer engagement, ultimately driving increased sales and reinforcing the brand's position in the industry.				Website Design Approval		Completed	01/02/24	Yes
					Development Completion		Completed	28/02/24	Yes
					Testing and QA		In Process	01/03/24	NA
					Launch		Not Started	10/04/24	NA
CONSTRAINTS					ASSUMPTIONS
Time Constraints: The project must adhere to a fixed timeline. / Budget Limitations: The project operates within a predefined budge. / Technical Dependencies: External APIs and technologies may introduce potential challenges. / Resource Availability: Availability of external resources may pose constraints. / Regulatory Compliance: Adherence to legal and industry regulations imposes constraints.					Timely Stakeholder Involvement: Assumes active and timely engagement from stakeholders. / Availability of External Resources: Assumes the availability and compatibility of external APIs and technologies required. / Smooth Team Collaboration: Assumes effective collaboration among the project team members.. / Accurate Product Information: Assumes timely availability of accurate product images and descriptions for catalog creation.

DELIVERABLES
A system allowing users to create accounts, manage preferences, and track order history. / Implementation of a robust order tracking system for customers to monitor the status of their purchases. / Comprehensive catalog showcasing high-quality resin products, including detailed descriptions and images. / Ensured compatibility and optimal user experience across various devices, emphasizing mobile responsiveness. / Implementation of a robust order tracking system for customers to monitor the status of their purchases.

SPONSOR NAME					SIGN & DATE
Nash Creations, Alpha2Marketing					20/12/23

## Plan
PROJECT PLAN
FairyDust Art
ADDRESS1	Sn 38/A Kharadkar Nagar, Opposite Bramha Suncity, New Kalyani Nagar, Pune, Maharashtra, India – 411014			Project Manager	Muiz Lambe
				Project Location	Pune, Maharashtra, India
ADDRESS2	Magarpatta City, Erica Society, Building Number D, Flat No 401, Pune, Maharashtra, India			Project Deliverables	Website With Its Products And Images
				Project Scope	Design and development of a mobile-responsive e-commerce website
CITY	Pune			Start Date	27/12/23
PHONE	918262003831			End Date	03/04/24
CONTACT NO.	020-26836912			EMAIL	nashcreations1@gmail.com

Activity/tasks
Sr. No	Activity/Task Name	Start Date	End Date	Duration(In Days)	Activity/Task Status	Budget
1	Presentation	29/12/23	02/01/24	5 days	Completed	$8000
2	Login/home page	03/01/24	10/01/24	7 days	Completed	$7000
3	Backend working	11/01/24	25/01/14	15 days	Completed	$14000
4	Datatbase Integration	26/01/24	31/01/24	5 days	In Progress	$6000
5	Cloud integration	01/02/24	10/02/24	10 days	In Progress	$5000
6	Product Addition	11/02/24	16/02/24	6 days	Not Started	$2000
7	Deployment	17/02/24	28/02/24	3 days	Not Started	$3000