## Charter
PROJECT CHARTER
PROJECT TITLE		TechMart Mobile App Development		PURPOSE		Enable TechMart customers to access products and services conveniently through a mobile application, enhancing their shopping experience.
DATE OF AUTHORIZATION		12/27/23		PROJECT START DATE		12/27/23		PROJECT END DATE		04/03/24
KEY SCHEDULE MILESTONES				CORE TEAM MEMBERS				KEY STAKEHOLDERS
UI/UX Design Finalization by March 1				NAME		ROLE		NAME		ROLE
Front End Development Kickoff by April 1				Muiz Lambe		Project Manager		Amar Sherkar		GMO
Backend Development needs to complete by August 1				Poonam Indalkar		Web Developer		Naved Shaikh		CEO
Beta Testing Phase Begins on September 1				Arshiya Shaikh		UI/UX Designer
User Acceptance Testing October 1				Safa Dalvi		Quality Assurance Tester
Launch Preparation and Marketing Campaign (October 15 - October 31)				Swaroop Bidkar		Marketing Specialist
OBJECTIVES
Develop a mobile application for TechMart customers to enhance their shopping experience and increase sales through a convenient and user-friendly platform.
GOALS					SUMMARY PROJECT STATUS
Increase customer engagement and loyalty by providing easy access to TechMart's products and services.					Budget			$45000
Improve sales and revenue by enabling customers to browse, purchase, and track orders seamlessly through the mobile app.					Project Start Date			12/27/23
					Project End Date			04/03/24
Enhance brand reputation and competitiveness in the e-commerce market by offering a modern and innovative mobile shopping solution.					Deployment			04/10/24
SCOPE			OPPORTUNITY				MIESTONES		STATUS	DUE	ASSIGNED TO
Design and develop a mobile application compatible with iOS and Android platforms.			Establish TechMart as a leader in digital innovation and customer-centricity within the e-commerce industry.				UI/UX Design		Completed	02/01/24	Arshiya Shaikh
					Frontend Development		Completed	02/28/24	Poonam Indalkar
					Backend Integration		In Progress	03/01/24	Poonam Indalkar
					Payment Gateway Integration		To-Do	04/10/24	Amar Sherkar
					Testing and QA		To-Do	06/18/24	Safa Dalvi
CONSTRAINTS					ASSUMPTIONS
Time Constraints: The project must adhere to a fixed timeline. / Budget Limitations: The project operates within a predefined budge. / Technical Dependencies: External APIs and technologies may introduce potential challenges. / Resource Availability: Availability of external resources may pose constraints. / Regulatory Compliance: Adherence to legal and industry regulations imposes constraints.					Availability of skilled developers, designers, and other team members required for the project.

DELIVERABLES
First Version of the Mobile App: Initial release with essential features and functionalities.

SPONSOR NAME					SIGN & DATE
Nash Creations, Alpha2Marketing					12/20/23

## Plan
PROJECT PLAN
TechMart Mobile App Development
ADDRESS1	Sn 38/A Kharadkar Nagar, Opposite Bramha Suncity, New Kalyani Nagar, Pune, Maharashtra, India – 411014			Project Manager	Muiz Lambe
				Project Location	Pune, Maharashtra, India
ADDRESS2	Magarpatta City, Erica Society, Pune, Maharashtra, India			Project Deliverables	First Version of the Mobile App: Initial release with essential features and functionalities.
				Project Scope	Design and develop a mobile application compatible with iOS and Android platforms.
CITY	Pune			Start Date	12/27/23
PHONE	918262003831			End Date	04/03/24
CONTACT NO.	020-26836912			EMAIL	nashcreations1@gmail.com

Activity/tasks
Sr. No	Activity/Task Name	Start Date	End Date	Duration(In Days)	Activity/Task Status	Budget
1	Presentation	12/29/23	01/02/24	5 days	Completed	$1000
2	Login	01/03/24	01/10/24	2 days	Completed	$7000
3	Home Page	02/04/24	01/11/24	3 days	In Progress	$1000
4	Registration	03/05/24	01/12/24	4 days	In Progress	$1000
5	About Us	07/06/24	01/13/24	5 days	Completed	$2000
6	Contact Us	11/07/24	01/14/24	6 days	Completed	$1000
7	Payment Gateway Integration	20/08/2024	01/15/24	7 days	Not Started	$1000
8	Add To Cart Page	01/09/24	01/16/24	8 days	Not Started	$1000
9	Backend working	01/11/24	01/25/14	15 days	Completed	$14000
10	Datatbase Integration	01/26/24	01/31/24	5 days	In Progress	$6000
11	Cloud integration	02/01/24	02/10/24	10 days	In Progress	$5000
12	Product Addition	02/11/24	02/16/24	6 days	Not Started	$2000
13	Deployment	02/17/24	02/28/24	3 days	Not Started	$3000