## Charter
PROJECT CHARTER
PROJECT TITLE		Udemy Learning Hub		PROJECT MANAGER		John Doe		PROJECT SPONSOR		Nash Creations
DATE OF AUTHORIZATION		01/10/24		PROJECT START DATE		01/10/24		PROJECT END DATE		06/30/24
SCOPE				CORE TEAM MEMBERS				KEY STAKEHOLDERS
Create a User-Friendly Interface				NAME		ROLE		NAME		ROLE
Content Development				Muiz Lambe		Project Manager		Amar Sherkar		GMO
Implement Learning Management System (LMS)				Poonam Indalkar		Web Developer		Naved Shaikh		CEO
Ensure Accessibility				Arshiya Shaikh		UI/UX Designer
Implement Feedback Mechanism				Safa Dalvi		Quality Assurance Tester
Launch Marketing Campaign				Swaroop Bidkar		Marketing Specialist
SPONSOR NAME					SIGN & DATE
Nash Creations, Alpha2Marketing					01/10/24

## Plan
PROJECT PLAN
Udemy Learning Hub
ADDRESS1	Sn 38/A Kharadkar Nagar, Opposite Bramha Suncity, New Kalyani Nagar, Pune, Maharashtra, India – 411014				Project Manager	Muiz Lambe
					Project Location	Pune, Maharashtra, India
ADDRESS2	Magarpatta City, Erica Society, Pune, Maharashtra, India				Project Deliverables	A fully functional education website featuring intuitive user interface, extensive course catalog, and interactive learning materials.
					Project Scope	Develop an online education platform providing diverse courses and resources for learners worldwide.
CITY	Pune				Start Date	01/10/24
PHONE	918262003831				End Date	06/30/24
BUDGET	$100,000.00				EMAIL	nashcreations1@gmail.com

Activity/tasks
Sr. No	Phase	Activity/Task Name	Start Date	End Date	Duration(In Days)	Activity/Task Status	Budget
1	Initiation	Define project scope and objectives	01/10/2024	01/15/2024	5 days	Completed	$5,000
		Identify stakeholders	01/10/2024	01/15/2024	5 days	In Progress	$3,000
		Develop project charter	01/10/2024	01/17/2024	7 days	In Progress	$7,000
2	Planning	Analyze user requirements	01/18/2024	01/25/2024	8 days	Not Started	$8,000
		Create wireframes and prototypes	01/20/2024	01/30/2024	10 days	Not Started	$10,000
		Develop content strategy	01/22/2024	01/28/2024	7 days	Not Started	$7,000
		Research and select LMS	01/25/2024	01/31/2024	7 days	Not Started	$6,000
3	Execution	Develop website frontend/backend	02/01/2024	02/28/2024	28 days	Not Started	$25,000
		Create/upload educational content	02/10/2024	03/15/2024	34 days	Not Started	$30,000
		Integrate LMS and configure processes	03/01/2024	03/15/2024	15 days	Not Started	$15,000
		Implement feedback mechanisms	03/10/2024	03/20/2024	11 days	Not Started	$10,000
4	Monitoring/Control	Monitor project progress	-	-	-	Not Started	-
		Track user engagement and feedback	-	-	-	Not Started	-
		Conduct quality assurance checks	-	-	-	Not Started	-
5	Closure	Obtain final approval	-	-	-	Not Started	-
		Document lessons learned	-	-	-	Not Started	-
		Hand over website to operational team	-	-	-	Not Started	-